## ReadMeFirst
INFO 8440 Team and Individual Project Plan, Time, Effort, Status Reporting Workbook
*** This is a sample, and a template ****
*** Teams submitting a RACI workbook that is not based on this Template will receive, at best, an Adequate rating ***
Created by: | Bill Nixon |  | Version | 5
History Table:
| Date | Version | Comments
| 2017-08-01 | 1 | Created and published
| 2019-10-17 | 2 | Added Actual RACI Columns, and Task Types
| 2018-12-01 | 3 | Added Person Sheets, and Daily Report
| 2021-01-21 | 4 | Created RACI Deliverables, and RACI Tasks sheets
| 2022-12-21 | 5 | Renamed sheets. Added more documentation and guidance.
Sheets
ReadMeFirst | This sheet. Gives an overview of the entire workbook
RACI Deliverables | Required. The latest version of the RACI Deliverables for the team for this project. This sheet is cloned at the first of every class day, and then updated.
RACI Tasks | Optional. The latest version of the RACI Tasks for the team for this project. This sheet is cloned at the first of every class day, and then updated.
Dlvrbls Day 3-1 | Required. The RACI Deliverables sheet as of Week 3 Day 1 at start of class. This should never be changed. Comparing this to the latest sheet will show the RACI changes, and thus team decisions.
By the time that the project is finished, there must be one backup sheet for each of all but the last 2 days (Briefing/Presentation Days) of the Project
Tasks Day 3-1 | Optional. The RACI Tasks sheet as of Week 3 Day 1 at start of class. This should never be changed.
Person1 | The Daily Time log for Person1 of the Team. Always insert new lines at the base of the list, so that the message at the bottom (Row 47 in the sampe) always stays.
** More Daily Log sheets needed - one for each team member! ** These should be kept in separate workbooks during the project, and submitted separately for final submission **
Gantt | Reserved Sheet for a Ecel based Gantt of the RACI Deliverables Sheet.
For the PM Docs version of this workbook, the Gantt will have no data, and thus no date range graphics, but it will have Excel formulas to create the graphics.
Guidance:
1) | Update RACI data only in the RACI sheet!
2) | The Activity Numbers in the Person Sheets are the code number for the Activity from the RACI
3) | All Required Deliverables for the Final Project submission must be provided in the Delvierables sheets. RFI and PM Docs Deliverable are optional.
4) | Every Deliverable Item must have a Responsible and Accountable person. It is allowable to be A,R, but someone else should do a Quality Check on all person's work.
5) | Formatting is left to you to do. This workbook is given to you as a guide. It must look different than this sample when submitted as INFO 8440 work.
6) | Save your work often. Save different versions of this file as backups.
7) | All dates must be formatted as DD-MMM or DD-MMM-YY 11-Jan-17 or 11-Jan
8) | The RACI-Actual Columns should only be filled in when the Actual differs from the Plan.
9) | Vlookup is used to echo the names of the deliverables into the Tasks sheets and the Gantt sheet
10) | Sheets are created to support filtering, not grouped reporting
11) | The Actual IsBuilt Date in RACI Deliverables indicates the date when the original creator has received a Quality OK rating from the team.
Usually, the component is then included in the final report and/or presentation
12) | In the RACI Deliverables and RACI Tasks sheets, from Row 7 and down, THERE MUST BE NO MERGED CELLS!
13) | Projected Effort data in the RACI+ Deliverables is expected in the Phase 3 Project, but optional in Phase 1
14) | The Deliverable Grouping is optional data.
15) | Minutes of Team Meetings are not required in this course. Instead, this RACI must be kept up to date, and backup sheets done every class day.
16) | This RACI+ workbook will be required as a weekly submission for later weeks in each project. Professor will provide details at that time.

## RACI Deliverables
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Report | A | Letter of Transmittal | 20 | R |  | A |  |  |  |  | 2022-03-25 | 2022-03-26 | 1
GA | Report | B | Cover Page | 20 |  |  | R | A |  |  |  | 2022-03-25 | 2022-03-26 | 1
GA | Report | C | Page Headers, Footers and Numbering | 20 | A | R | [5 empty] | 2022-03-25 | 2022-03-26 | 1
GA | Report | D | TOC | 20 |  |  |  | R | A |  |  | 2022-03-25 | 2022-03-26 | 1
GA | Report | E | Document History | 20 |  |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2
GA | Report | F | Executive Summary | 21 |  |  | R |  |  | A |  | 2022-03-31 | 2022-04-02 | 2
GA | Planning | G | Assumptions | 21 | R |  |  | A |  |  |  | 2022-03-31 | 2022-04-02 | 2
GA | Report | H | Conclusions | 21 |  | R |  |  |  | A |  | 2022-03-31 | 2022-04-02 | 2
GA | Report | I | Background and overview of client | 22 | A |  | R |  |  |  |  | 2022-03-31 | 2022-04-02 | 2
GA | Report | J | Requests for Information with NDA (included as an Appendix) | 23 | R | R | R | R | R | R |  | 2022-03-31 | 2022-04-02 | 2
GA | Planning | K | Project Scope Document | 24 |  | A | R |  |  |  |  | 2022-03-31 | 2022-04-02 | 2
GA | Planning | L | Business Challenges | 22 |  | A | R |  |  |  |  | 2022-03-31 | 2022-04-02 | 2
GA | Planning | M | Current Brands Involved and their Statuses | 22 |  |  |  | R | A |  |  | 2022-03-31 | 2022-04-02 | 2
GA | Report | N | Detailed References for all Sources of Knowledge | 23 |  | R |  | A |  |  |  | 2022-04-10 | 2022-04-21 | 11
GA | Deployment | O | Possible Future Analysis and Development for Call centre analysis | 26 |  |  |  |  | A | R |  | 2022-04-10 | 2022-04-21 | 11
GA | Planning | P | Measuring Success and Failure in call centre analysis | 26 |  |  | A |  | R |  |  | 2022-04-10 | 2022-04-21 | 11
GA | Planning | Q | Probable benefits of suggestions in the Call centre analysis | 26 |  |  |  | R |  | A |  | 2022-04-10 | 2022-04-21 | 11
GA | Planning | R | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | 1 |  | R | A |  |  |  |  | 2022-04-05 | 2022-04-18 | 13
GA | Planning | S | Data analysis operational Excel Report for CSR and Managers | 2 | R |  |  | A |  |  |  | 2022-04-05 | 2022-04-18 | 13
GA | Planning | T | AS-IS Process Flow | 3 |  |  | A |  |  | R |  | 2022-04-16 | 2022-04-20 | 4
GA | Deployment | U | To-Be Process flow | 3 |  |  |  |  | A | R |  | 2022-04-16 | 2022-04-20 | 4
GA | Planning | V | AS-IS Pseudocode | 3 |  |  |  |  | R | A |  | 2022-04-16 | 2022-04-20 | 4
GA | Deployment | W | To-Be Pseudocode | 3 | A |  |  |  | R |  |  | 2022-04-16 | 2022-04-20 | 4
GA | Planning | X | AS-IS Swimlanes | 3 |  | A |  | R | A |  |  | 2022-04-16 | 2022-04-20 | 4
GA | Deployment | Y | To-Be Swimlanes | 3 | A |  | R |  |  |  |  | 2022-04-16 | 2022-04-20 | 4
GA | Report | Z | Suggestion on changing staff report | 4 |  | R |  |  | A |  |  | 2022-04-13 | 2022-04-20 | 7
GA | Deployment | AA | Numerical Projection for Suggested Change in staff members | 4 |  |  | A |  | R |  |  | 2022-04-13 | 2022-04-20 | 7
GA | Deployment | AB | Detailed suggestion about Website technology | 5 | R |  | A |  |  |  |  | 2022-04-13 | 2022-04-20 | 7
GA | Deployment | AC | Suggestion Report on Infrastructure Upgradation | 6 | A |  |  |  |  | R |  | 2022-04-13 | 2022-04-20 | 7
GA | Planning | AD | Payrate Data and Model Calculations | 7 |  |  |  | R | A |  |  | 2022-04-13 | 2022-04-20 | 7
GA | Planning | AE | Gantt Chart | 25 |  | R | A |  |  |  |  | 2022-03-31 | 2022-04-02 | 2
GF | Report | AF | Merged Final Report | 29 | A |  | R |  |  |  |  | 2022-04-19 | 2022-04-22 | 3
GF | Report | AG | Powerpoint Presentation | 27 |  |  |  |  | A | R |  | 2022-04-19 | 2022-04-22 | 3
GF | Report | AH | Final RFI report | 23 | R | A | R |  |  |  |  | 2022-03-31 | 2022-04-20 | 20
GF | Report | AI | RACI+, Documentation, Backup Sheets | 25 |  | R | A |  |  |  |  | 2022-03-31 | 2022-04-20 | 20
GF | Report | AJ | Time and Effort Reporting | 25 | R | R | R | R | R | R |  | 2022-03-31 | 2022-04-20 | 20
0
0
0
0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 7 | 9 | 10 | 7 | 7 | 7
|  |  |  | A | 6 | 4 | 8 | 4 | 8 | 5
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## RACI Tasks
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [6 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | 1.1 | Letter of Transmittal | Develop a cover page | Create | R |  | A |  |  |  | 2022-03-25 | 2022-03-26 | 1
A | 1.2 | Letter of Transmittal | Develop a cover page | Pack and publish | R |  | A |  |  |  | 2022-03-25 | 2022-03-26 | 1
B | 2.1 | Cover Page | Develop a cover letter | Create |  |  | R | A |  |  | 2022-03-25 | 2022-03-26 | 1 |  |  | R | C | C
B | 2.2 | Cover Page | Develop a cover letter | Pack and publish |  |  | R | A |  |  | 2022-03-25 | 2022-03-26 | 1
C | 3.1 | Page Headers, Footers and Numbering | Develop a header, footer and numbering | Create | A | R |  |  |  |  | 2022-03-25 | 2022-03-26 | 1
C | 3.2 | Page Headers, Footers and Numbering | Develop header, footer and numbering | Pack and publish | A | R |  |  |  |  | 2022-03-25 | 2022-03-26 | 1
D | 4.1 | TOC | Create a table of content | Publish |  |  |  | R | A |  | 2022-03-25 | 2022-03-26 | 1
E | 5.1 | Document History | Research about documnent history document | Research |  |  |  |  | R | A | 2022-03-31 | 2022-04-02 | 2
E | 5.2 | Document History | Develop document history document | Create |  |  |  |  | R | A | 2022-03-31 | 2022-04-02 | 2
E | 5.3 | Document History | Publish document history document | Publish |  |  |  |  | R | A | 2022-03-31 | 2022-04-02 | 2
F | 6.1 | Executive Summary | Write summary for executives | Create |  |  | R |  |  | A | 2022-03-31 | 2022-04-02 | 2
F | 6.2 | Executive Summary | Publish summary for executive summary | Publish |  |  | R |  |  | A | 2022-03-31 | 2022-04-02 | 2
G | 7.1 | Assumptions | Gather assumptions | Create | R |  |  | A |  |  | 2022-03-31 | 2022-04-02 | 2
G | 7.2 | Assumptions | Create asuumptions | Research | R |  |  | A |  |  | 2022-03-31 | 2022-04-02 | 2
G | 7.3 | Assumptions | Publish assumptions | Pack and publish | R |  |  | A |  |  | 2022-03-31 | 2022-04-02 | 2
H | 8.1 | Conclusions | Create conclusion | Create |  | R |  |  |  | A | 2022-03-31 | 2022-04-02 | 2
H | 8.2 | Conclusions | Publish conclusion | Publish |  | R |  |  |  | A | 2022-03-31 | 2022-04-02 | 2
I | 9.1 | Background and overview of client | Develop document | Create | A |  | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
I | 9.2 | Background and overview of client | Publish final document | Publish | A |  | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
J | 10.1 | Requests for Information with NDA (included as an Appendix) | Create RFI Document | Create | R | R | R | R | R | R | 2022-03-31 | 2022-04-02 | 2
J | 10.2 | Requests for Information with NDA (included as an Appendix) | Look out for questions need to ask | Research | R | R | R | R | R | R | 2022-03-31 | 2022-04-02 | 2
J | 10.3 | Requests for Information with NDA (included as an Appendix) | Prepare Final RFI Document | Pack and publish | R | R | R | R | R | R | 2022-03-31 | 2022-04-02 | 2
K | 11.1 | Project Scope Document | Creating project scope | Create |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
K | 11.2 | Project Scope Document | Develop content for scope | Research |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
K | 11.3 | Project Scope Document | Finalize and publish | Pack and publish |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
L | 12.1 | Business Challenges | Creating business challenges in project document | Create |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
L | 12.2 | Business Challenges | Research about component | Research |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
L | 12.3 | Business Challenges | Publish and finalize | Pack and publish |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2
M | 13.1 | Current Brands Involved and their Statuses | Create current brand involved and statuses | Create |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2
M | 13.2 | Current Brands Involved and their Statuses | Prepare Decision flow | Research |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2
M | 13.3 | Current Brands Involved and their Statuses | Publish and finalize | Package and publish |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2
N | 14.1 | Detailed References for all Sources of Knowledge | Create all references from all sources | Create |  | R |  | A |  |  | 2022-04-10 | 2022-04-21 | 11
N | 14.2 | Detailed References for all Sources of Knowledge | Develop and research | Research |  | R |  | A |  |  | 2022-04-10 | 2022-04-21 | 11
N | 14.3 | Detailed References for all Sources of Knowledge | Publish and finalize | Package and publish |  | R |  | A |  |  | 2022-04-10 | 2022-04-21 | 11
O | 15.1 | Possible Future Analysis and Development for Call centre analysis | Develop list | Create |  |  |  |  | A | R | 2022-04-10 | 2022-04-21 | 11
O | 15.2 | Possible Future Analysis and Development for Call centre analysis | Publish | Package and publish |  |  |  |  | A | R | 2022-04-10 | 2022-04-21 | 11
p | 16.1 | Measuring Success and Failure in call centre analysis | Develop Document | Create |  |  | A |  | R |  | 2022-04-10 | 2022-04-21 | 11
p | 16.2 | Measuring Success and Failure in call centre analysis | Analyse and collect information | Research |  |  | A |  | R |  | 2022-04-10 | 2022-04-21 | 11
P | 16.3 | Measuring Success and Failure in call centre analysis | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-04-10 | 2022-04-21 | 11
Q | 17.1 | Probable benefits of suggestions in the Call centre analysis | Develop probable benefits of suggestions in call centre | Create |  |  |  | R |  | A | 2022-04-10 | 2022-04-21 | 11
Q | 17.2 | Probable benefits of suggestions in the Call centre analysis | Analyse and collect information | Research |  |  |  | R |  | A | 2022-04-10 | 2022-04-21 | 11
Q | 17.3 | Probable benefits of suggestions in the Call centre analysis | Finalize and publish | Package and publish |  |  |  | R |  | A | 2022-04-10 | 2022-04-21 | 11
R | 18.1 | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | Develop Document for data analysis of excel report for greeters,tech support and Experts | Create |  | R | A |  |  |  | 2022-04-05 | 2022-04-18 | 13
R | 18.2 | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | Analyse and collect information | Research |  | R | A |  |  |  | 2022-04-05 | 2022-04-18 | 13
R | 18.3 | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | Finalize and publish | Package and publish |  | R | A |  |  |  | 2022-04-05 | 2022-04-18 | 13
S | 19.1 | Data analysis operational Excel Report for CSR and Managers | Develop Document for data analysis of excel report for CSR and managers | Create | R |  |  | A |  |  | 2022-04-05 | 2022-04-18 | 13
S | 19.2 | Data analysis operational Excel Report for CSR and Managers | Finalize and publish | Package and publish | R |  |  | A |  |  | 2022-04-05 | 2022-04-18 | 13
T | 20.1 | AS-IS Process Flow | Develop Document | Create |  |  | A |  |  | R | 2022-04-16 | 2022-04-20 | 4
T | 20.2 | AS-IS Process Flow | Analyse and collect information | Research |  |  | A |  |  | R | 2022-04-16 | 2022-04-20 | 4
T | 20.3 | AS-IS Process Flow | Finalize and publish | Package and publish |  |  | A |  |  | R | 2022-04-16 | 2022-04-20 | 4
U | 21.1 | To-Be Process flow | Develop Document | Create |  |  |  |  | A | R | 2022-04-16 | 2022-04-20 | 4
U | 21.2 | To-Be Process flow | Analyse and collect information | Research |  |  |  |  | A | R | 2022-04-16 | 2022-04-20 | 4
U | 21.3 | To-Be Process flow | Finalize and publish | Package and publish |  |  |  |  | A | R | 2022-04-16 | 2022-04-20 | 4
V | 22.1 | AS-IS Pseudocode | Develop Document | Create |  |  |  |  | R | A | 2022-04-16 | 2022-04-20 | 4
V | 22.2 | AS-IS Pseudocode | Analyse and list out employee | Research |  |  |  |  | R | A | 2022-04-16 | 2022-04-20 | 4
V | 22.3 | AS-IS Pseudocode | Finalize and publish | Package and publish |  |  |  |  | R | A | 2022-04-16 | 2022-04-20 | 4
W | 23.1 | To-Be Pseudocode | Develop Document | Create | A |  |  |  | R |  | 2022-04-16 | 2022-04-20 | 4
w | 23.2 | To-Be Pseudocode | Finalize and publish | Package and publish | A |  |  |  | R |  | 2022-04-16 | 2022-04-20 | 4
X | 24.1 | AS-IS Swimlanes | Develop Document | Create |  | A |  | R | A |  | 2022-04-16 | 2022-04-20 | 4
X | 24.2 | AS-IS Swimlanes | Analyse and document | Research |  | A |  | R | A |  | 2022-04-16 | 2022-04-20 | 4
X | 24.3 | AS-IS Swimlanes | Finalize and publish | Package and publish |  | A |  | R | A |  | 2022-04-16 | 2022-04-20 | 4
Y | 25.1 | To-Be Swimlanes | Develop Document | Create | A |  | R |  |  |  | 2022-04-16 | 2022-04-20 | 4
Y | 25.2 | To-Be Swimlanes | Analyse and plan | Research | A |  | R |  |  |  | 2022-04-16 | 2022-04-20 | 4
Y | 25.3 | To-Be Swimlanes | Finalize and publish | Package and publish | A |  | R |  |  |  | 2022-04-16 | 2022-04-20 | 4
Z | 26.1 | Suggestion on changing staff report | Develop Document | Create |  | R |  |  | A |  | 2022-04-13 | 2022-04-20 | 7
Z | 26.2 | Suggestion on changing staff report | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-04-13 | 2022-04-20 | 7
AA | 27.1 | Numerical Projection for Suggested Change in staff members | Develop numerical projection sheet | Create |  |  | A |  | R |  | 2022-04-13 | 2022-04-20 | 7
AA | 27.2 | Numerical Projection for Suggested Change in staff members | Collect and analyze data from call centre data | Research |  |  | A |  | R |  | 2022-04-13 | 2022-04-20 | 7
AA | 27.3 | Numerical Projection for Suggested Change in staff members | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-04-13 | 2022-04-20 | 7
AB | 28.1 | Detailed suggestion about Website technology | Develop suggestion on website technology | Create | R |  | A |  |  |  | 2022-04-13 | 2022-04-20 | 7
AB | 28.2 | Detailed suggestion about Website technology | Collect and analyze data from call data analysis | Research | R |  | A |  |  |  | 2022-04-13 | 2022-04-20 | 7
AB | 28.3 | Detailed suggestion about Website technology | Finalize and publish | Package and publish | R |  | A |  |  |  | 2022-04-13 | 2022-04-20 | 7
AC | 29.1 | Suggestion Report on Infrastructure Upgradation | Develop suggestion report | Create | A |  |  |  |  | R | 2022-04-13 | 2022-04-20 | 7
AC | 29.2 | Suggestion Report on Infrastructure Upgradation | Collect and analyze data | Research | A |  |  |  |  | R | 2022-04-13 | 2022-04-20 | 7
AC | 29.3 | Suggestion Report on Infrastructure Upgradation | Finalize and publish | Package and publish | A |  |  |  |  | R | 2022-04-13 | 2022-04-20 | 7
AD | 30.1 | Payrate Data and Model Calculations | Develop payrate model | Create |  |  |  | R | A |  | 2022-04-13 | 2022-04-20 | 7
AD | 30.2 | Payrate Data and Model Calculations | analyze and collect information | Research |  |  |  | R | A |  | 2022-04-13 | 2022-04-20 | 7
AD | 30.3 | Payrate Data and Model Calculations | Publish | Package and publish |  |  |  | R | A |  | 2022-04-13 | 2022-04-20 | 7
AE | 31.1 | Gantt Chart | Plan all task schedules in project | Create |  | R | A |  |  |  | 2022-03-31 | 2022-04-02 | 2
AE | 31.2 | Gantt Chart | Publish | Package and publish |  | R | A |  |  |  | 2022-03-31 | 2022-04-02 | 2
AF | 32.1 | Merged Final Report | Create final report | Create | A |  | R |  |  |  | 2022-04-19 | 2022-04-22 | 3
AF | 32.2 | Merged Final Report | Prepare and Finalize | Package and publish | A |  | R |  |  |  | 2022-04-19 | 2022-04-22 | 3
AG | 33.1 | Powerpoint Presentation | Create final presentation | Create |  |  |  |  | A | R | 2022-04-19 | 2022-04-22 | 3
AG | 33.2 | Powerpoint Presentation | Prepare and Finalize | Package and publish |  |  |  |  | A | R | 2022-04-19 | 2022-04-22 | 3
AH | 34.1 | Final RFI report | Collect all information and prepare final document | Create | R | A | R |  |  |  | 2022-03-31 | 2022-04-20 | 20
AH | 34.2 | Final RFI report | Prepare and Finalize | Package and publish | R | A | R |  |  |  | 2022-03-31 | 2022-04-20 | 20
AI | 35.1 | RACI+, Documentation, Backup Sheets | Create document | Create |  | R | A |  |  |  | 2022-03-31 | 2022-04-20 | 20
AI | 35.2 | RACI+, Documentation, Backup Sheets | Finalize and publish | Package and publish |  | R | A |  |  |  | 2022-03-31 | 2022-04-20 | 20
AJ | 36.1 | Time and Effort Reporting | Develop document | Create | R | R | R | R | R | R | 2022-03-31 | 2022-04-20 | 20
AJ | 36.2 | Time and Effort Reporting | Log time and efforts | Research | R | R | R | R | R | R | 2022-03-31 | 2022-04-20 | 20
AJ | 36.3 | Time and Effort Reporting | Finalize and publish | Package and publish | R | R | R | R | R | R | 2022-03-31 | 2022-04-20 | 20
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 18 | 22 | 25 | 19 | 20 | 19
[7 empty] | A | 14 | 11 | 21 | 10 | 19 | 13
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Gantt sheet
TaskID | Task | Start date | End Date | Duration
A | Letter of Transmittal | 2022-03-25 | 2022-03-26 | 1
B | Cover Page | 2022-03-25 | 2022-03-26 | 1
C | Page Headers, Footers and Numbering | 2022-03-25 | 2022-03-26 | 1
D | TOC | 2022-03-25 | 2022-03-26 | 1
E | Document History | 2022-03-31 | 2022-04-02 | 2
F | Executive Summary | 2022-03-31 | 2022-04-02 | 2
G | Assumptions | 2022-03-31 | 2022-04-02 | 2
H | Conclusions | 2022-03-31 | 2022-04-02 | 2
I | Background and overview of client | 2022-03-31 | 2022-04-02 | 2
J | Requests for Information with NDA (included as an Appendix) | 2022-03-31 | 2022-04-02 | 2
K | Project Scope Document | 2022-03-31 | 2022-04-02 | 2
L | Business Challenges | 2022-03-31 | 2022-04-02 | 2
M | Current Brands Involved and their Statuses | 2022-03-31 | 2022-04-02 | 2
AE | Gantt Chart | 2022-03-31 | 2022-04-02 | 2
AH | Final RFI report | 2022-03-31 | 2022-04-20 | 20
AI | RACI+, Documentation, Backup Sheets | 2022-03-31 | 2022-04-20 | 20
AJ | Time and Effort Reporting | 2022-03-31 | 2022-04-20 | 20
R | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | 2022-04-05 | 2022-04-18 | 13
S | Data analysis operational Excel Report for CSR and Managers | 2022-04-05 | 2022-04-18 | 13
N | Detailed References for all Sources of Knowledge | 2022-04-10 | 2022-04-21 | 11
O | Possible Future Analysis and Development for Call centre analysis | 2022-04-10 | 2022-04-21 | 11
P | Measuring Success and Failure in call centre analysis | 2022-04-10 | 2022-04-21 | 11
Q | Probable benefits of suggestions in the Call centre analysis | 2022-04-10 | 2022-04-21 | 11
Z | Suggestion on changing staff report | 2022-04-13 | 2022-04-20 | 7
AA | Numerical Projection for Suggested Change in staff members | 2022-04-13 | 2022-04-20 | 7
AB | Detailed suggestion about Website technology | 2022-04-13 | 2022-04-20 | 7
AC | Suggestion Report on Infrastructure Upgradation | 2022-04-13 | 2022-04-20 | 7
AD | Payrate Data and Model Calculations | 2022-04-13 | 2022-04-20 | 7
T | AS-IS Process Flow | 2022-04-16 | 2022-04-20 | 4
U | To-Be Process flow | 2022-04-16 | 2022-04-20 | 4
V | AS-IS Pseudocode | 2022-04-16 | 2022-04-20 | 4
W | To-Be Pseudocode | 2022-04-16 | 2022-04-20 | 4
X | AS-IS Swimlanes | 2022-04-16 | 2022-04-20 | 4
Y | To-Be Swimlanes | 2022-04-16 | 2022-04-20 | 4
AF | Merged Final Report | 2022-04-19 | 2022-04-22 | 3
AG | Powerpoint Presentation | 2022-04-19 | 2022-04-22 | 3
Formulas:
Start date = VLOOKUP([TaskID],'RACI Deliverables'!$C7:O46,11,FALSE)
End Date = VLOOKUP([TaskID],'RACI Deliverables'!$C7:O46,12,FALSE)

## Dlvrbls Day 5-1 (hidden)
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2022-01-28
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak | Anusha Asokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya keesari
Deliverable Group |  | DlvID | Project Final Deliverables (RFIs and PM Docs Deliverables are optional) | Need / Requirement ID | MayurKum Plan | Prajwal Plan | Anusha A Plan | Jigeesha Plan | Cathleen Plan | Chaitanya keesari | Professor's Marking Item ID# | Start Date | Due Date (M/D/Y) | Actual Effort Days | Actual Start Date (M/D/Y) | Actual IsBuilt Date (M/D/Y) | Done On Date (M/D/Y)
GA | Building | A | Letter of Transmittal | 20 |  |  | A |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | B | Cover Page | 20 |  |  | R | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | C | Page Headers, Footers and Numbering | 20 | A | R | [5 empty] | 2022-01-27 | 2022-01-28 | 1
GA | Building | D | TOC | 20 |  |  |  | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | E | Document History | 20 |  |  |  |  | R | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | F | Executive Summary | 21 |  | A |  |  |  | R |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | G | Assumptions | 21 | R |  |  | A |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | H | Conclusions | 21 |  | R |  |  |  | A |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | I | Background and overview of client | 22 | A |  | R |  |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | J | Requests for Information with NDA (included as an Appendix) | 22 |  |  | A | R |  |  |  | 2022-01-20 | 2022-01-21 | 1
GA | Building | K | Project Scope Document | 24 | A | A |  | R |  |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | L | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Need7 | R | A | [5 empty] | 2022-02-03 | 2022-02-07 | 4
GA | Building | M | AS-IS principles of OHT and/or Executive Decision Making operations | Need7 |  |  | R |  | A |  |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | N | To-Be persons / roles / actors and interactions of Executive Decision Making operations | 43 |  |  |  | R |  | A |  | 2022-02-03 | 2022-02-07 | 4
GA | Building | O | Executive Dashboard annotated list of elements for the dashboard, | Need6 | R |  |  |  | A |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | P | Possible Future Analysis and Development for Executive Decision Making Process | 43 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | Q | Measuring Success and Failure in Changing the Executive Decision Making Process | 44 |  | A |  |  | R |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | R | Probable Benefits of Changing the Executive Decision Making Process | 46 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | S | Detailed References | 23 |  |  | R | A |  |  |  | 2022-02-10 | 2022-02-17 | 7
GA | Building | T | Business Challenges | 26 | R |  | A |  |  |  |  | 2022-02-03 | 2022-02-10 | 7
GA | Building | U | Current Brands Involved and their Statuses | 26 |  |  |  |  | A | R |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | V | Executive Dashboard Operation Process - 3+ Risks and Possible Mitigations | 26 |  |  |  | R |  | A |  | 2022-02-04 | 2022-02-10 | 6
GA | Building | W | Known Client Requirements | 41 |  | R |  |  | A |  |  | 2022-01-29 | 2022-02-06 | 8
GA | Building | X | Initial Project Scope in an Appendix, Changes to Scope in a Report Section | 45 |  |  | R | R | A |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Y | Gantt Chart |  | A | R |  |  | R |  |  | 2022-01-27 | 2022-01-28 | 1
GA | Building | Z | Document Quality Check |  | R | A | [5 empty] | 2022-02-15 | 2022-02-17 | 2
GA | Building | AA | USE CASE Diagram(s) for all involved persons, roles, actors, and systems showing their interactions | Need22 |  |  |  | A |  | R |  | 2022-02-04 | 2022-02-07 | 3
GA | Building | AC | Guidance on Using the Dashboard - Video or Text+Graphics | Need7 |  | R |  |  | A |  |  | 2022-02-08 | 2022-02-11 | 3
GA | Building | AD | TrackR Data Gen metric Data Sources List and DB Schema | Need7 | R | [6 empty] | 2022-02-05 | 2022-02-10 | 5
GA | Building | AE | TrackR Data Gen metric Data Sources Data Overview / Profile | Need7 |  | R |  | A |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AF | Executive Dashboard Style Guide for Navigation Principles, Colours, Fonts | Need8 |  |  |  | R | A |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | AG | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving forward | Need8 |  | A |  |  |  | R |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AH | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Moving backward | Need8 |  |  | A | R |  |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AI | Executive Dashboard Navigation Guide using Text, Wireframes and Mockups for Changing Time Frames | Need8 |  |  |  | A | R |  |  | 2022-02-08 | 2022-02-10 | 2
GA | Building | AJ | ERD Diagram | 49 | R | A | [5 empty] | 2022-02-04 | 2022-02-08 | 4
GA | Building | AM | Cockburn templates for all identified interactions | Need22 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-08 | 3
GA | Building | AN | List, References and General Details of Suggested Metrics | Need1 |  | R |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AO | Metric 1 - Data needed, Interpretation, Value to Decision Makers | Need1 | R |  |  |  |  | A |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AP | Metric 2 - Data needed, Interpretation, Value to Decision Makers | Need1 | A |  |  |  |  | R |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AQ | Metric 3 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  |  | A | R |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AR | Metric 4 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | R |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AS | Metric 5 - Data needed, Interpretation, Value to Decision Makers | Need1 |  | R |  |  | A |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AT | Metric 6 - Data needed, Interpretation, Value to Decision Makers | Need1 |  |  | A | R |  |  |  | 2022-02-05 | 2022-02-09 | 4
GA | Building | AU | Interview and/or survey of 6 OHT CPs | Need 2 | R | R | A |  |  |  |  | 2022-02-01 | 2022-02-03 | 2
GA | Building | AV | Data Listing of 6 OHT VPs Measurements of Business Success | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AW | Data Listing of 6 OHT VPs attitudes toward change, and cooperation in management | Need 2 |  |  | A |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AX | Data Listing of 6 OHT VPs visions for a better managed OHT | Need 2 |  |  |  |  | R | A |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AY | Data Listing of 6 OHT VPs Response to Meeting 3 times per week | Need 2 | A |  | R |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | AZ | Interview and/or survey of 6 OHT VPs | Need 3 |  | A |  |  |  | R |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BA | Data Listing of 6 OHT VPs Monthly Finance Reports Used | Need 3 |  |  |  | R | A |  |  | 2022-02-05 | 2022-02-10 | 5
GA | Building | BB | Listing of 6 OHT VPs Knowledge of Computer Based methods of Report Circulation | Need 3 |  |  |  | A |  | R |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BC | Listing of 6 OHT VPs Computer Skills, Dashboard Tech Understanding | Need 3 |  | R |  |  |  | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BD | Listing of 6 OHT VPs Preferred learning style | Need 3 |  |  | R | A |  |  |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BE | Listing of 6 OHT VPs Preferred ways to implement new concepts | Need 3 |  |  |  |  | R | A |  | 2022-02-07 | 2022-02-11 | 4
GA | Building | BF | VP's Written Briefing on Data Lakes, Data Marts, Data Warehouses, including SWOT | Need 4 |  |  | R |  |  | A |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BG | VP's Written Briefing on ERP. TPS and Query tools, with SWOT | Need 4 |  |  |  | R | A |  |  | 2022-02-03 | 2022-02-06 | 3
GA | Building | BH | VP's Written Briefing on Executive and Analytical Dashboards | Need 4 | R | A | [5 empty] | 2022-02-03 | 2022-02-06 | 3
GA | Building | BI | suggested plan background to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | R |  |  |  | A |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BJ | suggested plan vision to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | R |  |  | A |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BK | suggested VP training plans | Need 5 | A |  |  |  | R |  |  | 2022-02-11 | 2022-02-15 | 4
GA | Building | BL | suggested plan needs / requirements to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  |  | A |  | R |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BM | suggested plan actions to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  |  | A | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BN | suggested plan deliverables to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 |  | A | R |  |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BO | suggested plan resources to implement an Executive Dashboard with 5, at minimum, metrics | Need 5 | A |  |  | R |  |  |  | 2022-02-06 | 2022-02-10 | 4
GA | Building | BP | General configuration of Executive Dashboard using PowerBI | Need 6 |  | R | A |  |  |  |  | 2022-02-05 | 2022-02-10 | 5
GF | Closing | CA | RACI+, Documentation, Backup Sheets |  |  | R |  |  | A |  |  | 2022-01-28 | 2022-02-18 | 21
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
|  |  |  | R | 11 | 13 | 12 | 13 | 8 | 11
|  |  |  | A | 11 | 10 | 10 | 11 | 13 | 11
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany

## Tasks Day 5-1 (hidden)
Team Task Planning and Assignment Worksheet
Project Team (Assigned Group): |  |  | Team G | Course Week | Day
Date (Worksheet version): |  |  | 2020-09-17 | 3 | 2
[5 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari | [9 empty] | MayurKumar Rafaliya ( Project Manager) | Prajwal Nayak (RACI Keeper) | Anusha Ashokan Palat | Jigeesha Kocher | Cathleen Mathew Mundat | Chaitanya Keesari
DlvID | TaskID | Project Final Deliverables (No Verb Words at the start) | Activity / Task (VERB: Subject) | Project Phase (see WBS) | MayurKumar | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany | Start Date | Due Date (M/D/Y) | Actual Effort (Days) | Projected Effort (person - hrs) | Task Type - Team, Single or SubTeam | Task Version | Actual Start Date (M/D/Y) | Done On Date (M/D/Y) | RACI - ACTUAL
A | 1.1 | Letter of Transmittal | Develop a cover page | Create | R |  | A |  |  |  | 2022-03-25 | 2022-03-26 | 1 | #REF!
A | 1.2 | Letter of Transmittal | Develop a cover page | Pack and publish | R |  | A |  |  |  | 2022-03-25 | 2022-03-26 | 1 | #REF!
B | 2.1 | Cover Page | Develop a cover letter | Create |  |  | R | A |  |  | 2022-03-25 | 2022-03-26 | 1 | #REF! |  |  |  |  | R | C | C
B | 2.2 | Cover Page | Develop a cover letter | Pack and publish |  |  | R | A |  |  | 2022-03-25 | 2022-03-26 | 1 | #REF!
C | 3.1 | Page Headers, Footers and Numbering | Develop a header, footer and numbering | Create | A | R |  |  |  |  | 2022-03-25 | 2022-03-26 | 1 | #REF!
C | 3.2 | Page Headers, Footers and Numbering | Develop header, footer and numbering | Pack and publish | A | R |  |  |  |  | 2022-03-25 | 2022-03-26 | 1 | #REF!
D | 4.1 | TOC | Create a table of content | Publish |  |  |  | R | A |  | 2022-03-25 | 2022-03-26 | 1 | #REF!
E | 5.1 | Document History | Research about documnent history document | Research |  |  |  |  | R | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
E | 5.2 | Document History | Develoop document history document | Create |  |  |  |  | R | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
E | 5.3 | Document History | Publish document history document | Publish |  |  |  |  | R | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
F | 6.1 | Executive Summary | Write summary for executives | Create |  |  | R |  |  | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
F | 6.2 | Executive Summary | publish summary for executive summary | Publish |  |  | R |  |  | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
G | 7.1 | Assumptions | Gather assumptions | Research | R |  |  | A |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
G | 7.2 | Assumptions | Create asuumptions | Create | R |  |  | A |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
G | 7.3 | Assumptions | Publish assumptions | Pack and publish | R |  |  | A |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
H | 8.1 | Conclusions | Create conclusion | Create |  | R |  |  |  | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
H | 8.2 | Conclusions | Publish conclusion | Publish |  | R |  |  |  | A | 2022-03-31 | 2022-04-02 | 2 | #REF!
I | 9.1 | Background and overview of client | Develop document | Create | A |  | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
I | 9.2 | Background and overview of client | Publish final document | Publish | A |  | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
J | 10.1 | Requests for Information with NDA (included as an Appendix) | Create RFI Document | Create | R | R | R | R | R | R | 2022-03-31 | 2022-04-02 | 2 | #REF!
J | 10.2 | Requests for Information with NDA (included as an Appendix) | Look out for questions need to ask | Research | R | R | R | R | R | R | 2022-03-31 | 2022-04-02 | 2 | #REF!
J | 10.3 | Requests for Information with NDA (included as an Appendix) | Prepare Final RFI Document | Pack and publish | R | R | R | R | R | R | 2022-03-31 | 2022-04-02 | 2 | #REF!
K | 11.1 | Project Scope Document | Creating Document | Create |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
K | 11.2 | Project Scope Document | Develop content for scope | Research |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
K | 11.3 | Project Scope Document | Finalize and publish | Pack and publish |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
L | 12.1 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Interview VPs | Create |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
L | 12.2 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Prepare interactions flow of decision | Research |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
L | 12.3 | AS-IS persons / roles / actors and interactions of Executive Decision Making operations | Publish and finalize | Pack and publish |  | A | R |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
M | 13.1 | Current Brands Involved and their Statuses | Interview VPs | Create |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
M | 13.2 | Current Brands Involved and their Statuses | Prepare Decision flow | Research |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
M | 13.3 | Current Brands Involved and their Statuses | Publish and finalize | Package and publish |  |  |  | R | A |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
N | 14.1 | Detailed References for all Sources of Knowledge | Develop To-be flow | Create |  | R |  | A |  |  | 2022-04-10 | 2022-04-21 | 11 | #REF!
N | 14.2 | Detailed References for all Sources of Knowledge | Prepare interactions flow between actors/roles/system | Research |  | R |  | A |  |  | 2022-04-10 | 2022-04-21 | 11 | #REF!
N | 14.3 | Detailed References for all Sources of Knowledge | Publish and finalize | Package and publish |  | R |  | A |  |  | 2022-04-10 | 2022-04-21 | 11 | #REF!
O | 15.1 | Possible Future Analysis and Development for Call centre analysis | Develop list | Create |  |  |  |  | A | R | 2022-04-10 | 2022-04-21 | 11 | #REF!
O | 15.2 | Possible Future Analysis and Development for Call centre analysis | Publish | Package and publish |  |  |  |  | A | R | 2022-04-10 | 2022-04-21 | 11 | #REF!
p | 16.1 | Measuring Success and Failure in call centre analysis | Develop Document | Create |  |  | A |  | R |  | 2022-04-10 | 2022-04-21 | 11 | #REF!
p | 16.2 | Measuring Success and Failure in call centre analysis | Analyse and collect information | Research |  |  | A |  | R |  | 2022-04-10 | 2022-04-21 | 11 | #REF!
P | 16.3 | Measuring Success and Failure in call centre analysis | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-04-10 | 2022-04-21 | 11 | #REF!
Q | 17.1 | Probable benefits of suggestions in the Call centre analysis | Develop Document | Create |  |  |  | R |  | A | 2022-04-10 | 2022-04-21 | 11 | #REF!
Q | 17.2 | Probable benefits of suggestions in the Call centre analysis | Analyse and collect information | Research |  |  |  | R |  | A | 2022-04-10 | 2022-04-21 | 11 | #REF!
Q | 17.3 | Probable benefits of suggestions in the Call centre analysis | Finalize and publish | Package and publish |  |  |  | R |  | A | 2022-04-10 | 2022-04-21 | 11 | #REF!
R | 18.1 | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | Develop Document | Create |  | R | A |  |  |  | 2022-04-05 | 2022-04-18 | 13 | #REF!
R | 18.2 | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | Analyse and collect information | Research |  | R | A |  |  |  | 2022-04-05 | 2022-04-18 | 13 | #REF!
R | 18.3 | Data analysis operational Excel Report for Greeters, Tech Supports and Experts | Finalize and publish | Package and publish |  | R | A |  |  |  | 2022-04-05 | 2022-04-18 | 13 | #REF!
S | 19.1 | Data analysis operational Excel Report for CSR and Managers | Develop Document | Create | R |  |  | A |  |  | 2022-04-05 | 2022-04-18 | 13 | #REF!
S | 19.2 | Data analysis operational Excel Report for CSR and Managers | Finalize and publish | Package and publish | R |  |  | A |  |  | 2022-04-05 | 2022-04-18 | 13 | #REF!
T | 20.1 | AS-IS Process Flow | Develop Document | Create |  |  | A |  |  | R | 2022-04-16 | 2022-04-20 | 4 | #REF!
T | 20.2 | AS-IS Process Flow | Analyse and collect information | Research |  |  | A |  |  | R | 2022-04-16 | 2022-04-20 | 4 | #REF!
T | 20.3 | AS-IS Process Flow | Finalize and publish | Package and publish |  |  | A |  |  | R | 2022-04-16 | 2022-04-20 | 4 | #REF!
U | 21.1 | To-Be Process flow | Develop Document | Create |  |  |  |  | A | R | 2022-04-16 | 2022-04-20 | 4 | #REF!
U | 21.2 | To-Be Process flow | Analyse and collect information | Research |  |  |  |  | A | R | 2022-04-16 | 2022-04-20 | 4 | #REF!
U | 21.3 | To-Be Process flow | Finalize and publish | Package and publish |  |  |  |  | A | R | 2022-04-16 | 2022-04-20 | 4 | #REF!
V | 22.1 | AS-IS Pseudocode | Develop Document | Create |  |  |  |  | R | A | 2022-04-16 | 2022-04-20 | 4 | #REF!
V | 22.2 | AS-IS Pseudocode | Analyse and list out possible risks | Research |  |  |  |  | R | A | 2022-04-16 | 2022-04-20 | 4 | #REF!
V | 22.3 | AS-IS Pseudocode | Finalize and publish | Package and publish |  |  |  |  | R | A | 2022-04-16 | 2022-04-20 | 4 | #REF!
W | 23.1 | To-Be Pseudocode | Develop Document | Create | A |  |  |  | R |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
w | 23.2 | To-Be Pseudocode | Finalize and publish | Package and publish | A |  |  |  | R |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
X | 24.1 | AS-IS Swimlanes | Develop Document | Create |  | A |  | R | A |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
X | 24.2 | AS-IS Swimlanes | Analyse and document | Research |  | A |  | R | A |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
X | 24.3 | AS-IS Swimlanes | Finalize and publish | Package and publish |  | A |  | R | A |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
Y | 25.1 | To-Be Swimlanes | Develop Document | Create | A |  | R |  |  |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
Y | 25.2 | To-Be Swimlanes | Analyse and plan | Research | A |  | R |  |  |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
Y | 25.3 | To-Be Swimlanes | Finalize and publish | Package and publish | A |  | R |  |  |  | 2022-04-16 | 2022-04-20 | 4 | #REF!
Z | 26.1 | Suggestion on changing staff report | Develop Document | Create |  | R |  |  | A |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
Z | 26.2 | Suggestion on changing staff report | Finalize and publish | Package and publish |  | R |  |  | A |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AA | 27.1 | Numerical Projection for Suggested Change in staff members | Develop Use case Document | Create |  |  | A |  | R |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AA | 27.2 | Numerical Projection for Suggested Change in staff members | Analyse and list out relation between actors and systems | Research |  |  | A |  | R |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AA | 27.3 | Numerical Projection for Suggested Change in staff members | Finalize and publish | Package and publish |  |  | A |  | R |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AC | 29.1 | Suggestion Report on Infrastructure Upgradation | Record video for using dashboard | Create | A |  |  |  |  | R | 2022-04-13 | 2022-04-20 | 7 | #REF!
AC | 29.2 | Suggestion Report on Infrastructure Upgradation | Show step by step guidance on using dashboard | Research | A |  |  |  |  | R | 2022-04-13 | 2022-04-20 | 7 | #REF!
AC | 29.3 | Suggestion Report on Infrastructure Upgradation | Finalize and publish | Package and publish | A |  |  |  |  | R | 2022-04-13 | 2022-04-20 | 7 | #REF!
AD | 30.1 | Payrate Data and Model Calculations | Create source list | Create |  |  |  | R | A |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AD | 30.2 | Payrate Data and Model Calculations | analyze and collect information | Research |  |  |  | R | A |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AD | 30.3 | Payrate Data and Model Calculations | Publish | Package and publish |  |  |  | R | A |  | 2022-04-13 | 2022-04-20 | 7 | #REF!
AE | 31.1 | Gantt Chart | Create source list | Create |  | R | A |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
AE | 31.2 | Gantt Chart | Publish | Package and publish |  | R | A |  |  |  | 2022-03-31 | 2022-04-02 | 2 | #REF!
AF | 32.1 | Merged Final Report | Create document for style guide | Create | A |  | R |  |  |  | 2022-04-19 | 2022-04-22 | 3 | #REF!
AF | 32.2 | Merged Final Report | Prepare and Finalize | Package and publish | A |  | R |  |  |  | 2022-04-19 | 2022-04-22 | 3 | #REF!
AG | 33.1 | Powerpoint Presentation | Create navigation guide wireframe for moving forward | Create |  |  |  |  | A | R | 2022-04-19 | 2022-04-22 | 3 | #REF!
AG | 33.2 | Powerpoint Presentation | Prepare layout and finalize | Package and publish |  |  |  |  | A | R | 2022-04-19 | 2022-04-22 | 3 | #REF!
AH | 34.1 | Final RFI report | Create navigation guide wireframe for moving backward | Create | R | A | R |  |  |  | 2022-03-31 | 2022-04-20 | 20 | #REF!
AH | 34.2 | Final RFI report | Prepare layout and finalize | Package and publish | R | A | R |  |  |  | 2022-03-31 | 2022-04-20 | 20 | #REF!
AI | 35.1 | RACI+, Documentation, Backup Sheets | Create navigation guide wireframe for Changing time frame | Create |  | R | A |  |  |  | 2022-03-31 | 2022-04-20 | 20 | #REF!
AI | 35.2 | RACI+, Documentation, Backup Sheets | Prepare layout and finalize | Package and publish |  | R | A |  |  |  | 2022-03-31 | 2022-04-20 | 20 | #REF!
AJ | 36.1 | Time and Effort Reporting | Develop document | Create | R | R | R | R | R | R | 2022-03-31 | 2022-04-20 | 20 | #REF!
AJ | 36.2 | Time and Effort Reporting | Analyze and prepare erd layout | Research | R | R | R | R | R | R | 2022-03-31 | 2022-04-20 | 20 | #REF!
AJ | 36.3 | Time and Effort Reporting | Finalize and publish | Package and publish | R | R | R | R | R | R | 2022-03-31 | 2022-04-20 | 20 | #REF!
AM | 39.1 | #N/A | Develop Cockburn template | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AM | 39.2 | #N/A | Analyze and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AM | 39.3 | #N/A | Finalize and publish | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AN | 40.1 | #N/A | Create general details of suggested metrics | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AN | 40.2 | #N/A | Collect all information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AN | 40.3 | #N/A | Finalize and publish | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AO | 41.1 | #N/A | Develop document for Metric 1 | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AO | 41.2 | #N/A | Analyze and identify metric | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AO | 41.3 | #N/A | Prepare and Finalize | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AP | 42.1 | #N/A | Develop document for Metric 2 | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AP | 42.2 | #N/A | Analyze and identify metric | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AP | 42.3 | #N/A | Prepare and Finalize | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AQ | 43.1 | #N/A | Develop document for Metric 3 | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AQ | 43.2 | #N/A | Analyze and identify metric | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AQ | 43.3 | #N/A | Prepare and Finalize | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AR | 44.1 | #N/A | Develop document for Metric 4 | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! |  |  | 2017-09-08 | 2017-09-08 | R | R | R | R | R
AR | 44.2 | #N/A | Analyze and identify metric | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AR | 44.3 | #N/A | Prepare and Finalize | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AS | 45.1 | #N/A | Develop document for Metric 5 | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! |  |  | 2017-09-14 | 2017-09-14 | R | R | Absent | R | R
As | 45.2 | #N/A | Analyze and identify metric | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AS | 45.3 | #N/A | Prepare and Finalize | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AT | 46.1 | #N/A | Develop document for Metric 6 | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AT | 46.2 | #N/A | Analyze and identify metric | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AT | 46.3 | #N/A | Prepare and Finalize | Package and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AU | 47.1 | #N/A | Develop document | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AU | 47.2 | #N/A | Finalize document | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AV | 48.1 | #N/A | Develop document for business success | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AV | 48.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AV | 48.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AW | 49.1 | #N/A | Develop document for attitude towards change | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AW | 49.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AW | 49.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AX | 50.1 | #N/A | Develop document for OHT's vision for better management | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AX | 50.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AX | 50.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AY | 51.1 | #N/A | Develop document for response to meeting 3 times a week | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AY | 51.2 | #N/A | Analyse and collect information | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AY | 51.3 | #N/A | Finalize and Publish | Package and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AZ | 52.1 | #N/A | Develop document | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
AZ | 52.2 | #N/A | Finalize document | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BA | 53.1 | #N/A | Gather the infromation about Monthly Finance Reports used | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BA | 53.2 | #N/A | Document the infromation | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BA | 53.3 | #N/A | Finalise the report | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BB | 54.1 | #N/A | Gather the knowledge about the Computer Based methods of Report Circulation | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BB | 54.2 | #N/A | List the knowledge about the Computer Based methods of Report Circulation | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BB | 54.3 | #N/A | Publish the knowledge | Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BC | 55.1 | #N/A | Gather information about the computer skills, Dashboard understanding | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BC | 55.2 | #N/A | analyse information about the computer skills, Dashboard understanding | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BC | 55.3 | #N/A | Document the learning | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BD | 56.1 | #N/A | Eliciate the preferred way of learning a new concept from VP | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BD | 56.2 | #N/A | identify the way of learning | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BD | 56.3 | #N/A | Pack and publish preferred way of learning | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BE | 57.1 | #N/A | Eliciate the preferred way of implement a new concept from VP | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BE | 57.2 | #N/A | Identify the way of implementation | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BE | 57.3 | #N/A | Share it with a team | Pack and ublish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BF | 58.1 | #N/A | Research about the Data lakes, Data Marts, Data Warehouse, including SWOT | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BF | 58.2 | #N/A | Create about the Data lakes, Data Marts, Data Warehouse, including SWOT | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BF | 58.3 | #N/A | Pack and Publish the writtern briefing about Data lakes, Data Marts, Data Warehouse, including SWOT | Pack and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BG | 59.1 | #N/A | Research about the ERP, TPS and Query tools with SWOT | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BG | 59.2 | #N/A | Create about the ERP, TPS and Query tools with SWOT | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BG | 59.3 | #N/A | Pack and Publish the wirtten briefing about ERP, TPS and Query tools with SWOT | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BH | 60.1 | #N/A | Reserach about the analytical dashboard and Executive dashboard | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BH | 60.2 | #N/A | Create a report explaning analytical dashboard and Executive dashboard | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BH | 60.3 | #N/A | Pack and Publish the Report | Pack and publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BI | 61.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BI | 61.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BI | 61.3 | #N/A | Execute the implementation plan | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BJ | 62.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BJ | 62.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BJ | 62.3 | #N/A | Execute the implementation plan | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BK | 63.1 | #N/A | Research about the Training plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BK | 63.2 | #N/A | Create a Training plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BK | 63.3 | #N/A | Execute the training plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BL | 64.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BL | 64.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BL | 64.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BM | 65.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BM | 65.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BM | 65.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BN | 66.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BN | 66.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BN | 66.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BO | 67.1 | #N/A | Research and Plan about the implementation plan | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BO | 67.2 | #N/A | Create a implementation plan | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BO | 67.3 | #N/A | Execute the implementation plan | Execute | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BP | 68.1 | #N/A | Research about the General configuration of Executive Dashboard using PowerBI | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BP | 68.2 | #N/A | Create about the General configuration of Executive Dashboard using PowerBI | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
BP | 68.3 | #N/A | Pack and Publish General configuration of Executive Dashboard using PowerBI | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
CA | 79.1 | #N/A | Create a RACI+, Documentation and Backup Sheets | Research | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
CA | 79.2 | #N/A | Create a RACI+, Documentation and Backup Sheets | Create | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
CA | 79.3 | #N/A | Create a RACI+, Documentation and Backup Sheets | Pack and Publish | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF!
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany
[6 empty] | Analysis of Plan R, A, C, I's: | R | 15 | 22 | 25 | 19 | 20 | 19
[7 empty] | A | 14 | 11 | 18 | 10 | 19 | 13
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | I | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | MayurKum | Prajwal | Anusha A | Jigeesha | Cathleen | Chaitany